## Publication - PP Template
P000543 Henan Flood Emergency Rehabilitation and Recovery Project
Project Country: | China | Bank's Approval Date of the Initial Procurement Plan: | 07-30-2024
Project Sector: | Water | Approved PP Update No.: | Version 9
AIIB Loan (USD Million): | 1000.00 | Bank's Approval Date of the PP Update: | 2025-11-27
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Months) | Activity Status
Zhengzhou Project Management Office | ZZJTNCQX-Works-12 | Construction site: 27 townships, including Xinmi City, Dengfeng City, and Xinzheng City. Involving Yuanzhuang Township, Micun Town, Niudian Town, etc. Contents of works: restoration and construction of roadbed and pavement, protective drainage, traffic safety facilities, etc. Specific reparation: The road mileage is 102 kilometers, including 33.17 kilometers in Xinmi City, 51.43 kilometers in Dengfeng City, and 17.43 kilometers in Xinzheng City; The total length of safety facilities is 107.3 | 24,510,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-11-2024 | 04-29-2025 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-11 | Construction site: 25 townships, including Xingyang City, Gongyi City, and Zhongmu County. Involving Jiayu Town, Cuimiao Town, Liuhe Town, etc. Contents of works: restoration and construction of roadbed and pavement, protective drainage, traffic safety facilities, etc. Specific reparation: The road mileage is 114.3 kilometers, including 34.36 kilometers in Xingyang City, 67.59 kilometers in Gongyi City, and 12.32 kilometers in Zhongmu County; The total length of safety facilities is 114.3 kilo | 28,960,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-11-2024 | 04-29-2025 | 7 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Goods-21 | Automation control system equipment and installation | 980,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Post | No | 03-24-2025 | 08-05-2025 | 8 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Goods-1 | Construction of monitoring and perception system, construction of digital twin platform, construction of application system, etc. | 6,320,000.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Prior | No | 03-17-2025 | 07-29-2025 | 12 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Works-20 | River dredging, embankment filling, bank slope protection, ecological restoration within the blue line, one spoil area within the green line, Huaxi Gate, flood diversion gate, Fengqi Road bridge, Shangdu Road bridge, hydrological station relocation, ecological monitoring station relocation, long-distance optical cable, communication facility relocation, environmental protection and water conservation | 26,122,800.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-20-2024 | 09-20-2024 | 16 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Works-19 | River dredging, embankment filling, bank slope protection, ecological restoration within the blue line, three spoil areas within the green line, hydraulic dam, gas relocation, environmental protection and water conservation | 29,101,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-20-2024 | 09-20-2024 | 16 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Works-18 | River dredging, embankment filling, bank slope protection, ecological restoration within the blue line, Yangqiao main canal inverted siphon, Yangqiao main canal bridge, Baishi Guntan ditch gate, thermal relocation, one spoil area within the green line, Qiancheng Road bridge, tap water relocation under Qiancheng Road bridge, electricity relocation, environmental protection and water conservation | 34,038,700.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-20-2024 | 09-20-2024 | 16 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-10 | Construction site: Zhongmou. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 42 kilometers of pavement damaged by flood; demolition of new bridge 102.18 linear meters (4 bridges); 2 repaired bridges. | 10,420,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-26-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-09 | Construction site: Xinzheng. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 38.369 kilometers of roads damaged by flood; 3 new bridges; 1 repaired and reinforced bridge and 40 new culverts. | 17,270,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-26-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-08 | Construction site: Dengfeng. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 321 roads damaged by flood; 696.3 linear meters of new bridges and 15 repaired bridges damaged by flood; 77 culverts and 16030 meters of new concrete guardrails. | 29,240,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-26-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-07 | Construction site: Xinmi Xinhua Road sub district office, Chengguan Town, Quliang Town, Yuecun Town, Chaohua Town, Fuxi Mountain Scenic Spot Management Committee and other 16 counties (towns and offices) Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 207 kilometers of roads damaged by flood; 1082.68 linear meters of new bridges and 1 Bridge repaired; 55 culverts reconstructed and 2 culverts repaired. | 41,580,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-26-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-06 | Construction site: roads of Xinmi and Yuanzhuang County. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 123 kilometers of roads damaged by flood; 223.24 linear meters of new bridges and 4 bridges repaired; 2 culverts reconstructed and 4 culverts repaired. | 38,820,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-26-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-05 | Construction site: other counties of Gongyi. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 74 roads damaged by flood; 443.08 linear meters of new bridges and 8 repaired bridges damaged by flood; 15 new culverts. | 28,940,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 |  | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-04 | Construction site: Mihe County of Gongyi. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 28 bridges damaged by flood; 1081.1 linear meters of new bridges; 6 new culverts. | 32,610,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 |  | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-03 | Construction site: rural roads of Huancui District Management Committee, Gaoshan County, Sishui County, Liuhe County and Jiayu County in Xingyang. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 53.050 kilometers of roads damaged by flood; 1066.64 linear meters of new bridges; 176.08 linear meters of repaired and reinforced bridges; 17 new culverts. | 26,600,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-08-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-02 | Construction site: rural roads of Gaoxiang County, Guangwu County, Wangcun County, Cuimiao County, Jinzhai County, Chengguan County and Yulong County in Xingyang. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 77.36 kilometers of road damaged by flood; 721.27 linear meters of new bridges; 15 linear meters of repaired and reinforced bridges; 25 new culverts and 2 restored and reinforced culverts. | 27,670,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 08-25-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZJTNCQX-Works-01 | Construction site: part of roads in Xingyang. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 27.431 kilometers of roads damaged by flood; 450.254 linear meters of new bridges; 37.04 linear meters of repaired and reinforced bridges; 16 new culverts and 2 repaired and reinforced culverts. | 25,010,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-25-2022 | 09-23-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZPMO-Services-02 | Development, operation and maintenance of Management Information System.(combined with Xinxiang and Jiaozuo into one package) | 186,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 11-04-2022 | 2023-11-04 | 49 | Cleared
Zhengzhou Project Management Office | GCBCIP-Works-05 | YK0-750 ~ YK36+838 Works of desilting and dredging. | 2,100,000.00 | 100.00 | Works | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Post |  | 2022-04-30 | 05-30-2022 | 1 | Cleared
Zhengzhou Project Management Office | GCBCIP-Works-04 | Section YK29+200 ~ YK36+838: Works of embankment, desilting and dredging. | 5,020,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-29-2022 | 04-01-2023 | 6 | Cleared
Zhengzhou Project Management Office | GCBCIP-Works-03 | Section YK21+020 ~ YK29+200: Works of embankment, bridge, desilting and dredging. | 5,220,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-29-2022 | 04-01-2023 | 6 | Cleared
Zhengzhou Project Management Office | GCBCIP-Works-02 | Section YK9+500 ~ YK21+020: Works of embankment, bridge, desilting and dredging. | 3,500,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 6 | Cleared
Zhengzhou Project Management Office | GCBCIP-Works-01 | Section YK0-750 ~ YK9+500: Works of embankment, bridge, desilting and dredging. | 5,870,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-29-2022 | 04-01-2023 | 6 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Works-17 | The north side of 713 covers an area from the sideline (stake No. TH1+125) to the shooting range barrage (stake No. TH1+908) and flood diversion hub. The works include: river channel expansion and slope protection works, ecological restoration and ancillary facilities works, external dual power supply works, supporting buildings, shooting range barrage, Jinshui River flood diversion hub works, etc. | 42,120,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 12 | Cleared
Zhengzhou Project Management Office | ZZSLJSH-Works-16 | From the starting point of the project (stake No. TH0+000) to the side line of the occupied land in the north of 713 (stake No. TH1+125), the project content includes: river expansion and slope protection works, ecological restoration and ancillary facilities works, supporting buildings, etc. | 31,580,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 12 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-12 | Section: K12+039~K12+089; Contents of works: main structure of bridges, temporary access , demolition of temporary works, relocation of sewage pipelines etc. | 2,170,000.00 | 100.00 | Works | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Prior |  | 2022-01-21 | 02-21-2022 | 2 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-11 | Section: K7+535-K7+994.5, K15+080~K15+284; Contents of works: river works, bridge works, greening works, temporary works, pipeline protection, etc. | 7,660,000.00 | 100.00 | Works | RFQ (Request for Quotations) |  | Lowest Evaluated Cost | Prior |  | 2022-01-21 | 02-21-2022 | 2 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-10 | Section: K0+134.71~K22+261.6; Contents of works: external power access, including external cable path and box-type transformer from Guojiazui Reservoir to 10kV power supply point of Dongfengqu to box-type transformer substation in the residential quarters. | 3,340,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 09-14-2023 | 01-15-2024 | 8 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-09 | Section: K18+569.67~K22+261.6; Contents of works: landscape greening, decoration of bridges, power system, pavilions, public lavatories, landscape lamps and relocation of sewage pipelines, etc. | 21,720,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 10-28-2022 | 14 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-08 | Section: K14+392.42~K18+569.67; Contents of works: landscape greening, decoration of bridges, power system, pavilions, public lavatories, landscape lamps and relocation of sewage pipelines, etc. | 27,770,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 08-27-2022 | 14 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-07 | Section: K9+785.95~K14+392.42; Contents of works: landscape greening, power system, pavilions, public lavatories, underground garage in Changjiang Park, landscape lamps and relocation of sewage pipelines, etc. | 24,850,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 10-28-2022 | 14 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-06 | Section: K6+300.00~K9+785.95; Contents of works: landscape greening, power system, pavilions, public lavatories and landscape lamps etc. | 21,310,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 10-28-2022 | 14 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-05 | Section: K16+663.20~K22+261.6; Contents of works: river regulation, ecological improvement, boardwalks, bank revetments etc. | 30,640,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 10-28-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-04 | Section: K12+211~K16+663.20; Contents of works: river regulation, ecological improvement, boardwalks, bank revetments and sluices,etc. | 29,870,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 10-28-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-03 | Section: K6+300.00~K12+211.00; Contents of works: river regulation, ecological improvement, boardwalks, bank revetments and sluices, etc. | 32,110,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-27-2022 | 10-28-2022 | 7 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-02 | Section: K4+700~K6+300.00 Contents of works: in-channel and out-of-channel projects. | 8,340,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-07-2022 | 03-10-2023 | 7 | Cleared
Zhengzhou Project Management Office | ZZCJJSH-Works-01 | Section: K0+134.71~K1+479.34, K3+661.84~K4+105; Contents of works: in-channel and out-of-channel projects, including flood control project scope (K1+479.34~K3+661.84) water supply pipeline. | 18,920,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-07-2022 | 03-10-2023 | 7 | Cleared
Zhengzhou Project Management Office | ZZPMO-Services-03 | Hire a third-party external social and immigration monitoring company to ensure that good social and immigration management measures are followed during project implementation. Responsible for preparing external social and immigration monitoring reports that meet the requirements of the AIIB. | 90,000.00 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 11-04-2022 | 01-02-2023 | 49 | Cleared
Zhengzhou Project Management Office | ZZPMO-Services-04 | Hire a third-party external environmental monitoring company to ensure that good environmental management measures are followed during project implementation. Responsible for preparing external environmental monitoring reports that meet the requirements of the AIIB. | 90,000.00 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 11-04-2022 | 01-02-2023 | 49 | Cleared
Zhengzhou Project Management Office | ZZPMO-Services-01 | Hire a professional consulting service agency to approve the project management level of PMO and supervise the project implementation management. | 2,634,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 06-07-2022 | 11-04-2022 | 49 | Cleared
Jiaozuo Project Management Office | JZSB203 | Jiaozuo Smart Water Environment Platform (Flood Control) Platform | 1,776,214.29 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Prior | No | 01-15-2026 | 05-29-2026 | 12 | Cleared
Jiaozuo Project Management Office | JZSB202 | Jiaozuo Smart Water Conservancy Platform | 1,699,757.14 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Prior | No | 01-15-2026 | 05-29-2026 | 12 | Cleared
Jiaozuo Project Management Office | JZSB201 | Jiaozuo Monitoring and Early Warning Emergency Command Platform | 2,007,600.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Prior | No | 01-15-2026 | 05-29-2026 | 12 | Cleared
Jiaozuo Project Management Office | JZZX304 | Development, Operation and Maintenance Services for Management Information System (MIS) | 128,571.43 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 04-15-2022 | 08-27-2022 | 14 | Cleared
Jiaozuo Project Management Office | JZZX303 | Select social and immigration external monitoring unit | 171,428.57 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 12-14-2022 | 02-11-2023 | 39 | Cleared
Jiaozuo Project Management Office | JZZX302 | Select external environmental monitoring unit | 171,428.57 | 100.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) |  | Post |  | 12-14-2022 | 02-11-2023 | 42 | Cleared
Jiaozuo Project Management Office | JZZX304 | procurement of Management Information System (Centralized procurement by Xinxiang City) | 128,571.43 | 100.00 | Consulting Services | NCS (National Competitive Selection) | QBS (Quality Based Selection) |  | Prior |  | 04-15-2022 | 09-09-2022 | 42 | Cancel-Cleared
Jiaozuo Project Management Office | JZZX301 | Select consulting units with international financial organization project management experience | 2,385,714.29 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 04-15-2022 | 09-09-2022 | 58 | Cleared
Jiaozuo Project Management Office | JZTJ121B | Tianjiangou River Rehabilitation Project (Linyuan Road -Puji River) | 5,239,585.71 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-26-2024 | 09-25-2024 | 9 | Cleared
Jiaozuo Project Management Office | JZTJ121A | Tianjiangou River Rehabilitation Project (Jiefang West Road to Linyuan Road) | 5,212,285.71 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 07-26-2024 | 09-25-2024 | 9 | Cleared
Jiaozuo Project Management Office | JZTJ120 | Rehabilitation of Jiefang East Road Project | 10,388,041.73 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 8 | Cleared
Jiaozuo Project Management Office | JZTJ119 | Rehabilitation of Jianshe Road Project | 2,795,208.12 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 10 | Cleared
Jiaozuo Project Management Office | JZTJ118 | Rehabilitation of Jiaowu Road Project | 727,871.27 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 6 | Cleared
Jiaozuo Project Management Office | JZTJ117 | Rehabilitation of Gongye Road Project | 6,420,868.31 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 12 | Cleared
Jiaozuo Project Management Office | JZTJ116 | Rehabilitation of Minzhu Road Project | 2,543,079.59 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 12 | Cleared
Jiaozuo Project Management Office | JZTJ115 | Rehabilitation of Fengshou Road Project | 5,389,500.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 10 | Cleared
Jiaozuo Project Management Office | JZTJ114 | Rehabilitation of Longyuan Road (Minzhu road ~ Shanyang Road) Project | 4,606,233.20 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 12 | Cleared
Jiaozuo Project Management Office | JZTJ113 | Rehabilitation of Shanyang Road (Taihang Road to Jianshe Road) Project | 5,851,960.09 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 13 | Cleared
Jiaozuo Project Management Office | JZTJ112 | Rehabilitation of Beihuan Road (Puji road ~ Tabei Road) Project | 8,597,164.49 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 12 | Cleared
Jiaozuo Project Management Office | JZTJ111 | Urban River Bridge Flood Control Capacity Improvement Project | 3,276,682.99 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-16-2023 | 03-18-2023 | 9 | Cleared
Jiaozuo Project Management Office | JZTJ110 | Improvement of Flood Discharge Capacity of Urban Flood Intercepting Ditch and New Build Project | 4,623,332.03 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-16-2023 | 06-19-2023 | 10 | Cleared
Jiaozuo Project Management Office | JZTJ109 | Urban Road Sporadic Flood Damage Restoration Project | 2,325,880.49 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 11-09-2022 | 03-12-2023 | 8 | Cleared
Jiaozuo Project Management Office | JZTJ108 | Urban Drainage Pipe Network Inspection and Repair Project | 7,945,042.76 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 02-16-2023 | 04-18-2023 | 17 | Cleared
Jiaozuo Project Management Office | JZTJ107 | Urban River Facility Rehabilitation Project | 1,352,795.84 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 01-16-2023 | 05-19-2023 | 7 | Cleared
Jiaozuo Project Management Office | JZTJ106 | Qunying River Disaster Recovery Project | 9,815,596.67 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-16-2023 | 06-19-2023 | 12 | Cleared
Jiaozuo Project Management Office | JZTJ105 | Wengjian River (Beihuan Road to Shanyang Road) Disaster Recovery Project | 3,164,772.22 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-16-2023 | 06-19-2023 | 9 | Cleared
Jiaozuo Project Management Office | JZTJ104 | Rehabilitation of Shanmen River in Macun District, Jiaozuo City | 15,714,285.71 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-01-2022 | 04-03-2023 | 12 | Cleared
Jiaozuo Project Management Office | JZTJ103 | Rehabilitation of Shanmen River Damaged by Flood in Xiuwu County | 4,073,457.14 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-01-2022 | 04-03-2023 | 10 | Cleared
Jiaozuo Project Management Office | JZTJ102B | Rehabilitation of Dasha River Damaged by Flood in Xiuwu County (From Yuntai Avenue Construction Bridge to Jiao - Xin boundary) | 6,650,242.86 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-01-2022 | 04-03-2023 | 16 | Cleared
Jiaozuo Project Management Office | JZTJ102A | Rehabilitation of Dasha River Damaged by Flood in Xiuwu County (Starting point of Xiuwu Dasha River to Yuntai Avenue Construction Bridge) | 7,571,428.57 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-01-2022 | 04-03-2023 | 16 | Cleared
Jiaozuo Project Management Office | JZTJ101C | Rehabilitation of Dasha River Damaged by Flood in Jiaozuo City (New construction of Nanzhang Road Bridge) | 6,000,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-06-2022 | 04-08-2023 | 16 | Cleared
Jiaozuo Project Management Office | JZTJ101B | Rehabilitation of Dasha River Damaged by Flood in Jiaozuo City (Xinyue Railway Section - 2.5km downstream of Jiugao Road) | 16,000,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-06-2022 | 04-08-2023 | 16 | Cleared
Jiaozuo Project Management Office | JZTJ101A | Rehabilitation of Dasha River Damaged by Flood in Jiaozuo City (Chushankou - Xinyue Railway Section) | 15,000,000.00 | 100.00 | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 12-06-2022 | 04-08-2023 | 16 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXZJ-Works-2 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of Rainwater Pumping Station at Hongli Avenue and the East Mengjiangnu River Section II | 23,811,714.29 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-30-2025 | 10-31-2025 | 28 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXZJ-Works-1 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of Rainwater Pumping Station at Hongli Avenue and the East Mengjiangnu River Section I | 11,300,557.14 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-30-2025 | 10-31-2025 | 12 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXCG-Works-4 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Xiangyang Rainwater Pumping Station Section II | 17,601,644.63 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-16-2025 | 10-17-2025 | 12 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXCG-Works-3 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Xiangyang Rainwater Pumping Station Section I | 21,107,372.57 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-16-2025 | 10-17-2025 | 16 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXCG-Works-2 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Yinmakaou Rainwater Pumping Station Section II | 21,139,030.93 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-16-2025 | 10-17-2025 | 16 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXCG-Works-1 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Yinmakaou Rainwater Pumping Station Section I | 20,915,488.83 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-16-2025 | 10-17-2025 | 16 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXYJ-Goods-1 | Xinxiang Emergency Platform Building Project | 4,346,385.71 |  | Goods | NCT (National Competitive Tendering) |  | Rated Criteria | Prior | No | 11-14-2024 | 03-28-2025 | 16 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXPMO-Services-1 | Project Management Consulting Firm | 1,318,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 04-22-2022 | 09-03-2022 | 47 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | WHSL-Works-1 | Weihui Cang River Downstream Rehabilitation Works | 15,960,152.00 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 05-11-2024 | 09-11-2024 | 42 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXPMO-Services-2 | Development , Operation and Maintenance Services for Management Information System (MIS) | 110,571.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Post |  | 04-15-2022 | 08-27-2022 | 1 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGJ-Goods-4 | Procurement of 10m Electric Buses ×50 | 6,071,429.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-02-2022 | 10-03-2022 | 1 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGJ-Goods-3 | Procurement of 75 Electric Buses (10m Electric Buses×50， 6m Electric Buses×25) | 7,785,714.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-02-2022 | 10-03-2022 | 1 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGJ-Goods-2 | Procurement of 79 Electric Buses (11m Electric Buses×20， 8m Electric Buses×59) | 7,571,429.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 06-02-2022 | 10-03-2022 | 1 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGJ-Goods-1 | Procurement of Electric Cars Charging Piles and Supporting Power Supply Equipment | 2,470,971.00 | 100.00 | Goods | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 12-06-2022 | 02-05-2023 | 2 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGJ-Works-1 | Bus Terminal Ground Surface Rehabilitation and Hardening, and Construction of 2-Floor Office Building Project | 3,624,143.00 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Post | No | 12-01-2022 | 01-31-2023 | 6 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGL-Works-4 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section IV) | 25,644,243.00 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-02-2022 | 08-03-2022 | 7 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGL-Works-3 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section III) | 15,821,534.00 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-02-2022 | 08-03-2022 | 7 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGL-Works-2 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section II) | 21,050,127.00 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-02-2022 | 08-03-2022 | 7 | Cleared
Office of the Xinxiang Project Leading Group of the AIIB Financed Henan Flood Emergency Rehabilitation and Recovery Project | XXGL-Works-1 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section I) | 18,480,425.00 |  | Works | NCT (National Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 04-02-2022 | 08-03-2022 | 7 | Cleared
|  | Total: | 1,171,188,033.32