## Sheet1
[Project Number][Project Name] | P000543 Henan Flood Emergency Rehabilitation and Recovery Project
Project Country: | China
Project Sector: | Water
AIIB Loan (EUR Million): | 865 | Bank's Approval Date of the PP Update: | 2025-05-28
Project Implementing Entity: | Zhengzhou Project Management Office Jiaozuo Project Management Office Xinxiang Project Management Office
PROJECT PROCUREMENT PLAN
Contract Number | Contract Description | Cost Estimate in USD | Procurement Category | Procurement Method | Particular Selection Method | Bank Review (Prior/Post) | Contract Duration (Month) | Activity Status
XXZJ-Works-2 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of Rainwater Pumping Station at Hongli Avenue and the East Mengjiangnu River Section II | 23,811,714.29 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
XXZJ-Works-1 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of Rainwater Pumping Station at Hongli Avenue and the East Mengjiangnu River Section I | 11,300,557.14 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
XXCG-Works-4 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Xiangyang Rainwater Pumping Station Section II | 17,601,644.63 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
XXCG-Works-3 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Xiangyang Rainwater Pumping Station Section I | 21,107,372.57 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
XXCG-Works-2 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Yinmakaou Rainwater Pumping Station Section II | 21,139,030.93 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
XXCG-Works-1 | Improvement of Xinxiang Urban Drainage System Project for the Catchment Area of the Yinmakaou Rainwater Pumping Station Section I | 20,915,488.83 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
XXYJ-Goods-1 | Xinxiang Emergency Platform Building Project | 4,346,385.71 | Goods | NCT (National Competitive Tendering) | Rated Criteria | Prior Review |  | Cleared
ZZJTNCQX-Works-12 | Construction site: 27 townships, including Xinmi City, Dengfeng City, and Xinzheng City. Involving Yuanzhuang Township, Micun Town, Niudian Town, etc. Contents of works: restoration and construction of roadbed and pavement, protective drainage, traffic safety facilities, etc. Specific reparation: The road mileage is 102 kilometers, including 33.17 kilometers in Xinmi City, 51.43 kilometers in Dengfeng City, and 17.43 kilometers in Xinzheng City; The total length of safety facilities is 107.3 | 24,510,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-11 | Construction site: 25 townships, including Xingyang City, Gongyi City, and Zhongmu County. Involving Jiayu Town, Cuimiao Town, Liuhe Town, etc. Contents of works: restoration and construction of roadbed and pavement, protective drainage, traffic safety facilities, etc. Specific reparation: The road mileage is 114.3 kilometers, including 34.36 kilometers in Xingyang City, 67.59 kilometers in Gongyi City, and 12.32 kilometers in Zhongmu County; The total length of safety facilities is 114.3 kilo | 28,960,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZSLJSH-Goods-21 | Automation control system equipment and installation | 980,000.00 | Goods | NCT (National Competitive Tendering) | Rated Criteria | Post Review | 8 | Cleared
ZZSLJSH-Goods-1 | Construction of monitoring and perception system, construction of digital twin platform, construction of application system, etc. | 6,320,000.00 | Goods | NCT (National Competitive Tendering) | Rated Criteria | Prior Review | 12 | Cleared
ZZSLJSH-Works-20 | River dredging, embankment filling, bank slope protection, ecological restoration within the blue line, one spoil area within the green line, Huaxi Gate, flood diversion gate, Fengqi Road bridge, Shangdu Road bridge, hydrological station relocation, ecological monitoring station relocation, long-distance optical cable, communication facility relocation, environmental protection and water conservation | 26,122,800.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
ZZSLJSH-Works-19 | River dredging, embankment filling, bank slope protection, ecological restoration within the blue line, three spoil areas within the green line, hydraulic dam, gas relocation, environmental protection and water conservation | 29,101,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
ZZSLJSH-Works-18 | River dredging, embankment filling, bank slope protection, ecological restoration within the blue line, Yangqiao main canal inverted siphon, Yangqiao main canal bridge, Baishi Guntan ditch gate, thermal relocation, one spoil area within the green line, Qiancheng Road bridge, tap water relocation under Qiancheng Road bridge, electricity relocation, environmental protection and water conservation | 34,038,700.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
JZZX304 | Development, Operation and Maintenance Services for Management Information System (MIS) | 128,571.43 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Post Review | 42 | Cleared
ZZJTNCQX-Works-10 | Construction site: Zhongmou. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 42 kilometers of pavement damaged by flood; demolition of new bridge 102.18 linear meters (4 bridges); 2 repaired bridges. | 10,420,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-09 | Construction site: Xinzheng. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 38.369 kilometers of roads damaged by flood; 3 new bridges; 1 repaired and reinforced bridge and 40 new culverts. | 17,270,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-08 | Construction site: Dengfeng. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 321 roads damaged by flood; 696.3 linear meters of new bridges and 15 repaired bridges damaged by flood; 77 culverts and 16030 meters of new concrete guardrails. | 29,240,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-07 | Construction site: Xinmi Xinhua Road sub district office, Chengguan Town, Quliang Town, Yuecun Town, Chaohua Town, Fuxi Mountain Scenic Spot Management Committee and other 16 counties (towns and offices) Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 207 kilometers of roads damaged by flood; 1082.68 linear meters of new bridges and 1 Bridge repaired; 55 culverts reconstructed and 2 culverts repaired. | 41,580,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-06 | Construction site: roads of Xinmi and Yuanzhuang County. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 123 kilometers of roads damaged by flood; 223.24 linear meters of new bridges and 4 bridges repaired; 2 culverts reconstructed and 4 culverts repaired. | 38,820,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-05 | Construction site: other counties of Gongyi. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 74 roads damaged by flood; 443.08 linear meters of new bridges and 8 repaired bridges damaged by flood; 15 new culverts. | 28,940,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-04 | Construction site: Mihe County of Gongyi. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 28 bridges damaged by flood; 1081.1 linear meters of new bridges; 6 new culverts. | 32,610,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-03 | Construction site: rural roads of Huancui District Management Committee, Gaoshan County, Sishui County, Liuhe County and Jiayu County in Xingyang. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 53.050 kilometers of roads damaged by flood; 1066.64 linear meters of new bridges; 176.08 linear meters of repaired and reinforced bridges; 17 new culverts. | 26,600,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-02 | Construction site: rural roads of Gaoxiang County, Guangwu County, Wangcun County, Cuimiao County, Jinzhai County, Chengguan County and Yulong County in Xingyang. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 77.36 kilometers of road damaged by flood; 721.27 linear meters of new bridges; 15 linear meters of repaired and reinforced bridges; 25 new culverts and 2 restored and reinforced culverts. | 27,670,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZJTNCQX-Works-01 | Construction site: part of roads in Xingyang. Contents of works: earthwork of subgrade, bridges, culverts, protective drainage, traffic safety facilities, etc. Specific reparation: 27.431 kilometers of roads damaged by flood; 450.254 linear meters of new bridges; 37.04 linear meters of repaired and reinforced bridges; 16 new culverts and 2 repaired and reinforced culverts. | 25,010,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZPMO-Services-02 | Development, operation and maintenance of Management Information System.(combined with Xinxiang and Jiaozuo into one package) | 186,000.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Prior Review | 49 | Cleared
GCBCIP-Works-05 | YK0-750 ~ YK36+838 Works of desilting and dredging. | 2,100,000.00 | Civil Works | RFQ (Request for Quotations) | Lowest Evaluated Cost | Post Review | 1 | Cleared
GCBCIP-Works-04 | Section YK29+200 ~ YK36+838: Works of embankment, desilting and dredging. | 5,020,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 6 | Cleared
GCBCIP-Works-03 | Section YK21+020 ~ YK29+200: Works of embankment, bridge, desilting and dredging. | 5,220,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 6 | Cleared
GCBCIP-Works-02 | Section YK9+500 ~ YK21+020: Works of embankment, bridge, desilting and dredging. | 3,500,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 6 | Cleared
GCBCIP-Works-01 | Section YK0-750 ~ YK9+500: Works of embankment, bridge, desilting and dredging. | 5,870,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 6 | Cleared
ZZSLJSH-Works-17 | The north side of 713 covers an area from the sideline (stake No. TH1+125) to the shooting range barrage (stake No. TH1+908) and flood diversion hub. The works include: river channel expansion and slope protection works, ecological restoration and ancillary facilities works, external dual power supply works, supporting buildings, shooting range barrage, Jinshui River flood diversion hub works, etc. | 42,120,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
ZZSLJSH-Works-16 | From the starting point of the project (stake No. TH0+000) to the side line of the occupied land in the north of 713 (stake No. TH1+125), the project content includes: river expansion and slope protection works, ecological restoration and ancillary facilities works, supporting buildings, etc. | 31,580,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
ZZCJJSH-Works-12 | Section: K12+039~K12+089; Contents of works: main structure of bridges, temporary access , demolition of temporary works, relocation of sewage pipelines etc. | 2,170,000.00 | Civil Works | RFQ (Request for Quotations) | Lowest Evaluated Cost | Prior Review | 2 | Cleared
ZZCJJSH-Works-11 | Section: K7+535-K7+994.5, K15+080~K15+284; Contents of works: river works, bridge works, greening works, temporary works, pipeline protection, etc. | 7,660,000.00 | Civil Works | RFQ (Request for Quotations) | Lowest Evaluated Cost | Prior Review | 2 | Cleared
ZZCJJSH-Works-10 | Section: K0+134.71~K22+261.6; Contents of works: external power access, including external cable path and box-type transformer from Guojiazui Reservoir to 10kV power supply point of Dongfengqu to box-type transformer substation in the residential quarters. | 3,340,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 8 | Cleared
ZZCJJSH-Works-09 | Section: K18+569.67~K22+261.6; Contents of works: landscape greening, decoration of bridges, power system, pavilions, public lavatories, landscape lamps and relocation of sewage pipelines, etc. | 21,720,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 14 | Cleared
ZZCJJSH-Works-08 | Section: K14+392.42~K18+569.67; Contents of works: landscape greening, decoration of bridges, power system, pavilions, public lavatories, landscape lamps and relocation of sewage pipelines, etc. | 27,770,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 14 | Cleared
ZZCJJSH-Works-07 | Section: K9+785.95~K14+392.42; Contents of works: landscape greening, power system, pavilions, public lavatories, underground garage in Changjiang Park, landscape lamps and relocation of sewage pipelines, etc. | 24,850,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 14 | Cleared
ZZCJJSH-Works-06 | Section: K6+300.00~K9+785.95; Contents of works: landscape greening, power system, pavilions, public lavatories and landscape lamps etc. | 21,310,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 14 | Cleared
ZZCJJSH-Works-05 | Section: K16+663.20~K22+261.6; Contents of works: river regulation, ecological improvement, boardwalks, bank revetments etc. | 30,640,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZCJJSH-Works-04 | Section: K12+211~K16+663.20; Contents of works: river regulation, ecological improvement, boardwalks, bank revetments and sluices,etc. | 29,870,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZCJJSH-Works-03 | Section: K6+300.00~K12+211.00; Contents of works: river regulation, ecological improvement, boardwalks, bank revetments and sluices, etc. | 32,110,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZCJJSH-Works-02 | Section: K4+700~K6+300.00 Contents of works: in-channel and out-of-channel projects. | 8,340,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZCJJSH-Works-01 | Section: K0+134.71~K1+479.34, K3+661.84~K4+105; Contents of works: in-channel and out-of-channel projects, including flood control project scope (K1+479.34~K3+661.84) water supply pipeline. | 18,920,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
ZZPMO-Services-03 | Hire a third-party external social and immigration monitoring company to ensure that good social and immigration management measures are followed during project implementation. Responsible for preparing external social and immigration monitoring reports that meet the requirements of the AIIB. | 90,000.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) | Post Review | 49 | Cleared
ZZPMO-Services-04 | Hire a third-party external environmental monitoring company to ensure that good environmental management measures are followed during project implementation. Responsible for preparing external environmental monitoring reports that meet the requirements of the AIIB. | 90,000.00 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) | Post Review | 49 | Cleared
ZZPMO-Services-01 | Hire a professional consulting service agency to approve the project management level of PMO and supervise the project implementation management. | 2,634,000.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Prior Review | 49 | Cleared
JZZX303 | Select social and immigration external monitoring unit | 171,428.57 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) | Post Review | 39 | Cleared
JZZX302 | Select external environmental monitoring unit | 171,428.57 | Consulting Services | LC (Limited Competition) | CQS (Consultant's Qualification Based Selection) | Post Review | 39 | Cleared
XXPMO-Services-1 | Project Management Consulting Firm | 1,318,000.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Post Review | 47 | Cleared
JZZX301 | Select consulting units with international financial organization project management experience | 2,385,714.29 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Prior Review | 58 | Cleared
WHSL-Works-1 | Weihui Cang River Downstream Rehabilitation Works | 15,960,152.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
XXPMO-Services-2 | Development , Operation and Maintenance Services for Management Information System (MIS) | 110,571.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) | Post Review | 42 | Cleared
XXGJ-Goods-4 | Procurement of 10m Electric Buses ×50 | 6,071,429.00 | Goods | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 1 | Cleared
XXGJ-Goods-3 | Procurement of 75 Electric Buses (10m Electric Buses×50， 6m Electric Buses×25) | 7,785,714.00 | Goods | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 1 | Cleared
XXGJ-Goods-2 | Procurement of 79 Electric Buses (11m Electric Buses×20， 8m Electric Buses×59) | 7,571,429.00 | Goods | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 1 | Cleared
XXGJ-Goods-1 | Procurement of Electric Cars Charging Piles and Supporting Power Supply Equipment | 2,470,971.00 | Goods | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 2 | Cleared
XXGJ-Works-1 | Bus Terminal Ground Surface Rehabilitation and Hardening, and Construction of 2-Floor Office Building Project | 3,624,143.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 6 | Cleared
XXGL-Works-4 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section IV) | 25,644,243.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
XXGL-Works-3 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section III) | 15,821,534.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
XXGL-Works-2 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section II) | 21,050,127.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
XXGL-Works-1 | Xinxiang National and Provincial Disaster Destroyed Highways Recovery and Reconstruction Project (Section I) | 18,480,425.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 7 | Cleared
JZTJ121B | Tianjiangou River Rehabilitation Project (Linyuan Road -Puji River) | 5,239,585.71 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 9 | Cleared
JZTJ121A | Tianjiangou River Rehabilitation Project (Jiefang West Road to Linyuan Road) | 5,212,285.71 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 9 | Cleared
JZTJ120 | Rehabilitation of Jiefang East Road Project | 10,388,041.73 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 8 | Cleared
JZTJ119 | Rehabilitation of Jianshe Road Project | 2,795,208.12 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 10 | Cleared
JZTJ118 | Rehabilitation of Jiaowu Road Project | 727,871.27 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 6 | Cleared
JZTJ117 | Rehabilitation of Gongye Road Project | 6,420,868.31 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
JZTJ116 | Rehabilitation of Minzhu Road Project | 2,543,079.59 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
JZTJ115 | Rehabilitation of Fengshou Road Project | 5,389,500.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 10 | Cleared
JZTJ114 | Rehabilitation of Longyuan Road (Minzhu road ~ Shanyang Road) Project | 4,606,233.20 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
JZTJ113 | Rehabilitation of Shanyang Road (Taihang Road to Jianshe Road) Project | 5,851,960.09 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 13 | Cleared
JZTJ112 | Rehabilitation of Beihuan Road (Puji road ~ Tabei Road) Project | 8,597,164.49 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
JZTJ111 | Urban River Bridge Flood Control Capacity Improvement Project | 3,276,682.99 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 9 | Cleared
JZTJ110 | Improvement of Flood Discharge Capacity of Urban Flood Intercepting Ditch and New Build Project | 4,623,332.03 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 10 | Cleared
JZTJ109 | Urban Road Sporadic Flood Damage Restoration Project | 2,325,880.49 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 8 | Cleared
JZTJ108 | Urban Drainage Pipe Network Inspection and Repair Project | 7,945,042.76 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 17 | Cleared
JZTJ107 | Urban River Facility Rehabilitation Project | 1,352,795.84 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Post Review | 7 | Cleared
JZTJ106 | Qunying River Disaster Recovery Project | 9,815,596.67 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
JZTJ105 | Wengjian River (Beihuan Road to Shanyang Road) Disaster Recovery Project | 3,164,772.22 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 9 | Cleared
JZTJ104 | Rehabilitation of Shanmen River in Macun District, Jiaozuo City | 15,714,285.71 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 12 | Cleared
JZTJ103 | Rehabilitation of Shanmen River Damaged by Flood in Xiuwu County | 4,073,457.14 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 10 | Cleared
JZTJ102B | Rehabilitation of Dasha River Damaged by Flood in Xiuwu County (From Yuntai Avenue Construction Bridge to Jiao - Xin boundary) | 6,650,242.86 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
JZTJ102A | Rehabilitation of Dasha River Damaged by Flood in Xiuwu County (Starting point of Xiuwu Dasha River to Yuntai Avenue Construction Bridge) | 7,571,428.57 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
JZTJ101C | Rehabilitation of Dasha River Damaged by Flood in Jiaozuo City (New construction of Nanzhang Road Bridge) | 6,000,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
JZTJ101B | Rehabilitation of Dasha River Damaged by Flood in Jiaozuo City (Xinyue Railway Section - 2.5km downstream of Jiugao Road) | 16,000,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared
JZTJ101A | Rehabilitation of Dasha River Damaged by Flood in Jiaozuo City (Chushankou - Xinyue Railway Section) | 15,000,000.00 | Civil Works | NCT (National Competitive Tendering) | Lowest Evaluated Cost | Prior Review | 16 | Cleared