## III-Works
Project Name: Mumbai Urban Transport Project III
Procurement Plan: Works
| Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [13 empty] | Revision No.17 |  | Revision Date: | 07.04.2025
Specific Procurement Arrangements | [11 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status
Serial No. | Contract No. | Description of Contract | Cost Estimate in Local Currency without GST (In INR crore) | Cost Estimate in USD (In million) | Funding* Source by AIIB (%) (Excluding Taxes) | Funding* Source by Others (%) (includes Taxes & Rly Funding) | Procurement Category | Procurement Method (IOCT/DC/ST/ NCT/ RFQ) | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency (In INR crore) including GST | Contract Price Equivalence in USD (In million) | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
A |  | Works
Engineering Works
Virar-Dahanu Road
1 | MRVC/W/101 | Quadrupling of Railway Track between Virar - Dahanu Road under MUTP-III.” LOT I Construction of Major bridges, Minor Bridges, Drains, retaining wall, extension of Limited height Subway/RUB, Ballast supply and Earthwork in the section from Ch. 2060 to Ch. 9000 and From Ch. 16800 to CH. 30,000 between Virar (Excluding) and Palghar (Excluding) | 210 | 30 | 100 | 15 | Works | IOCT | Prior | No | No | 11/19 | 11/20 | 200.6 | 28.66 | M/s Relcon-Vitrag JV, Mumbai, Maharashtra | India | 17/11/2020 | 36 Extended up to 31.12.2025 | Under Implementation
|  | LOT II Construction of Major bridges, Minor Bridges, Drains, retaining wall, extension of Limited height Subway/RUB, Ballast supply and Earthwork in the section from Ch. 32100 to Ch. 61400 between Palghar Station (Excluding) and Dahanu Road Station (Excluding) | 180 | 25.71 | [5 empty] | No | No | 11/19 | 11/20 | 210.22 | 30.03 | M/s NG Project Ltd. NG Circle, Mehtapura, Himmatnagar, Dist. Sabarkantha, Gujrat | India | 17/11/2020 | 36 Extension to completion period is under process of sanction | Under Implementation
2 | MRVC/W/102 | “Execution of P-Way / Track Linking works including Supply of P.Way Materials (excluding Supply of Rails & PSC main line Sleepers), Yard Remodeling, Laying of turnouts, SEJ and other miscellaneous works in connection with Virar - Dahanu Road Quadrupling Project under MUTP-III” in Two Lots. LOT-I : Virar South yard (including) to Palghar North yard (Including). RFT No: MRVC/W/102/LOT-I | 107.0382 | 1.338 | 100 | 15 | Works | NCT | Prior | No | No | 07/24 | 12/24 | 147.72 | 18.465 | M/s Miral Infrastructure Nikol, Ahemdabad |  |  | 24
|  | “Execution of P-Way / Track Linking works including Supply of P.Way Materials (excluding Supply of Rails & PSC main line Sleepers), Yard Remodeling, Laying of turnouts, SEJ and other miscellaneous works in connection with Virar - Dahanu Road Quadrupling Project under MUTP-III” in Two Lots. LOT-II : Palghar North yard (Excluding) to Dahanu North yard (Including). RFT No: MRVC/W/102/LOT-II | 83.4127 | 1.0427 | 100 | 15 | Works | NCT | Prior | No | No | 07/24 | 12/24 | 102.5 | 12.8125 | M/s SCPL-SPMPL (JV), Odissa, Bhubaneshwar |  |  | 24
3 | MRVC/W/103* | Construction of Important Bridge No.92 & 93, Major bridge No.98,99,166 & 169, Minor Bridge No.95, 96, 97, 100 & 101 including sub structure and super structure, Earthwork in embankment, cutting, drains, retaining walls from(km 68/22 to km 75/24) Ch: 9000 to 16000(excluding Saphale) for VR-DRD quadrupling work of Mumbai division and construction of Bridge No- 92 and 93 in lieu of existing Bridge No- 92 and 93*. | 648.42 | 92.63 | 51 | 49 | Works | IOCT | Prior | No | No | 09/20 | 06/21 | 611.96 | 87.42 | M/s Venkata Rao Infra Projects Pvt. Ltd., Visakhapatnam, Andhra Pradesh | India | 18/06/2021 | 36 | Under Implementation
4 | MRVC/W/104/R | Construction of Station buildings, service buildings, New Platforms, New FOBs, Staff quarters, Tower wagon shed; Extension of existing platforms, existing FOBs, bridges; earthwork for Railway formation including associated General Electrification works and OHE works; and dismantling of existing structures at various stations in connection with Quadrupling of Virar-Dahanu Road through 3 LOTs. LOT-I: All Proposed structures in the section between Virar (Including) and Vaitarana (Including) Stations RFT No. MRVC/W/104/LOT I | 177 | 25.29 | 100 | 15 | Works | NOCT | Prior | No | No | 02/22 | 11/22 | 203.57 | 29.08 | M/s. Saidutta Manisha (JV) | India | 15/11/2022 | 36 | Under Implementation
5 | MRVC/W/104/R1 | Construction of Station buildings, service buildings, New Platforms, New FOBs, Staff quarters, Tower wagon shed; Extension of existing platforms, existing FOBs, bridges; earthwork for Railway formation; and dismantling of existing structures at various stations in connection with Quadrupling of Virar-Dahanu Road through 2 LOTs. LOT II: All Proposed structures in the section between Vaitarana (Excluding) – Palghar (Including) Stations RFT No. MRVC/W/104/R1/LOT II | 184 | 26.29 | 100 | 15 | Works | IOCT | Prior | No | No | 10/22 | 04/23 | 208.42 | 29.77 | M/s Relcon Infraprojects, Mumbai, Maharashtra | India | 21/04/23 | 36 | Under Implementation
|  | LOT III: All Proposed structures in the section between Palghar (Excluding ) – Dahanu Road (Including) Stations RFT No. MRVC/W/104/R1/LOT III | 220 | 31.43 | [5 empty] | No | No |  | 04/23 | 279.66 | 39.95 | M/s Vitrag-Relcon JV, Mumbai, Maharashtra | India | 21/4/23 | 36 | Under Implementation
6 | MRVC/W/129 | Construction of ROB in lieu of L.C. No. 55a in the section between Vangaon and Dahanuroad stations in connection with Quadrupling of Virar Dahanu Road Project In Mumbai Central Division of Western Railway. | 40 | 5.71 | 100 | 15 | Works | NOCT | Post | No | No | 09/22 | 02/23 | 38.89 | 5.56 | M/s Saidutt Real Infra,Mumbai, Maharastra | India | 2023-06-04 | 24 | Under Implementation
7 | MRVC/W/139 | “Providing P-Way/Track Linking works including Supply of PWay Materials (excluding Rails and Sleepers) and Supply of Ballast, Yard Remodeling, Laying of turnouts, SEJ and other miscellaneous works in Tarapur siding for proposed Goods Depot in connection with VR-DRD Quadrupling Project under “MUTP-III”. | 3.562 | 0.050886 | 100 | 15 | Works | NOCT | Post | No | No | 06/ 24 | 11/ 24 | 3.98 | 0.56857 | M/s Sai Projects (Mumbai) Pvt. Ltd. | India | 15/1/25 | 12 | Under Implementation
|  | Sub total Engineering works ( Virar Dahanu ) | 1853.4329 | 239.4915 | [9 empty] | 2007.52 | 282.3161
Panvel-Karjat
8 | MRVC/W/107 | Construction of formation in Embankment and Cutting, Blanketing, Rock cutting, Construction of Major & Minor Bridges, RUBs, ROBs, Construction of Drain/ Retaining wall, Ballast Supply and Removal of Infringements in Panvel-Karjat section in connection with Panvel – Karjat double line Suburban Corridor under MUTP-III in 2 LOTs. LOT-I: From Ch: 00+000 (Km) to Ch: 15+000 (Km). | 187 | 26.71 | 100 | 15 | Works | IOCT | Prior | No | No | 11/19 | 12/20 | 192.91 | 27.56 | M/s. Thakur Infraprojects Pvt. Ltd. ,New Mumbai, Maharashtra | India | 23/12/2020 | 36 Extended upto 31.12.2024 | Under Implementation
|  | LOT-II: From Ch: 15+000 (Km) to Ch: 29+600 (Km). | 210 | 30 | [5 empty] | No | No | 11/19 | 12/20 | 185 | 26.43 | RELCON-SREPL (JV) Mumbai, Maharashtra | India | 23/12/2020 | 36 Extended upto 31.05.2025 | Under Implementation
9 | MRVC/W/108A | Panvel to Karjat: Station buildings, service buildings, Platforms, FOBs, staff quarters etc. including general electrification works (Except Chikhale, Mohape , Chowk and Karjat Stations) in connection with Panvel-Karjat double line suburban corridor project under MUTP –III | 138 | 19.71 | 100 | 15 | Works | NOCT | Prior | No | No | 08/22 | 04/23 | 142.77 | 20.4 | MIRAL-SCGPL JV | India | 15/04/2023 | 36 | Under Implementation
10 | MRVC/W/108B | Panvel - Karjat suburban corridor: Station buildings, service buildings, Platforms, FOBs etc. at Chikhle, Mohape, Chowk and Karjat stations | 127 | 18.14 | 100 | 15 | Works | NOCT | Prior | No | No | 03/23 | 09/23 | 142.39 | 17.8 | M/s KD AND PARTNERS (JV) | India | 2023-09-12 | 24 | Under Implementation
11 | MRVC/W/109 | Construction of Rail Fly Over at Panvel , KJT Approach, 2 ROBs and Pune Expressway RUB | 376 | 53.71 | 100 | 15 | Works | IOCT | Prior | No | Yes | 06/19 | 12/19 | 374.8 | 53.54 | M/s. M. Venkata Rao Infra Projects Pvt. Ltd.,Vishakhapatnam, Andhra Pradesh | India | 2020-09-03 | 36 | Under Implementation
12 | MRVC/W/110 | Wavarle, Nadhal and Kirawali Tunnel and Aproach cutting, Retaining wall, Drain etc Tunnel Ventilation and Lighting | 354 | 50.57 | 100 | 15 | Works | IOCT | Prior | No | No | 04/21 | 02/22 | 297.36 | 42.48 | M/s. SDPL-TIPL - JMMIPL JV, Anudh, Pune | India | 14/02/2022 | 36 | Under Implementation
13 | MRVC/W/111 | Panvel Karjat Suburban corridor:Track linking & Supply of Track Fittings including turnouts and SEJs, balance Ballast Supply and Transportation etc. | 78 | 11.14 | 100 | 15 | Works | NOCT | Post | No | No | 02/24 | 06/24 | 59.59 | 8.512 | NMC-NSP(JV) | India | 24/09/2024 | 24 | Under Implementation
|  | Sub total Engineering works ( Panvel Karjat ) | 1470 | 209.98 | [9 empty] | 1394.82 | 196.722
Mid-Section tress pas control
14 | MRVC/W2/MUTP-3/Midsection/104-R2 | Central Railway- CSMT to Kasara: Construction of FOBs and Associated Works to control Mid-Section Tress passing | 40.4 | 5.77 | 100 | 15 | Works | IOCT | Prior | No | Yes | 09/17 | 02/18 | 40.45 | 5.78 | M/s Koneru Construction Pvt. Ltd. Vijayawada, Andhra Pradesh | India | 2018-01-02 | 18 | Under Implementation
15 | MRVC/W2/MUTP-3/Midsection/103-R2 | Central Railway- Kalyan-Karjat including Ambernath & Badlapur: Construction of FOBs and Associated Works to control Mid-Section Tress passing | 53.75 | 7.68 | 100 | 15 | Works | IOCT | Prior | No | Yes | 09/18 | 02/19 | 53.75 | 7.68 | Maharashtra Steel Fabricators Thane, Maharashtra | India | 2019-01-02 | 18 | Under Implementation
16 | MRVC/MTCM/NCB/W/MUTP-III/DR | Western Railway- Churchgate to Virar: Construction of FOBs and Associated Works to control Mid-Section Tress passing | 73.72 | 10.53 | 100 | 15 | Works | IOCT | Prior | No | Yes | 06/18 | 11/18 | 73.73 | 10.53 | M/s. Sai Projects Pvt. Ltd. , Mumbai, Maharashtra | India | 27/11/2018 | 18 | Under Implementation
17 | MRVC/MTCM/NCB/W/MUTP-III/D9 | Harbour Line- Sewri to Panvel: Construction of FOBs and Associated Works to control Mid-Section Tress passing | 41.08 | 5.87 | 100 | 15 | Works | IOCT | Prior | No | Yes | 05/18 | 05/18 | 18.97 | 2.71 | M/s Kailashchand Pvt. Ltd. , New Mumbai, Maharashtra | India | 31/05/2018 | 18 | Work completed
18 | MRVC/W/125 | Mid-Section Tresspass Control Measures under MUTP III C. Rly, "Completion of balance work of Construction of FOBs, Skywalk, Platform with Shelter, Linkway, Booking office, Station Building, Quarters, Toilet Blocks, Boundry wall, Pathway and other works in connection with Tresspass control at various location in Kalyan - Karjat section. | 44 | 6.29 | 100 | 15 | Works | NOCT | Post | No | No | 11/21 | 03/22 | 50.18 | 6.4 | M/s. SAI PROJECTS (Mumbai) Pvt. Ltd. Khar (West) Mumbai-400052 | India | 25/03/2022 | 24 | Under Implementation
19 | MRVC/W/131 | Construction of FOBs and Associated Works to control Mid-Section Tress passing at different locations of Mumbai division (7 FoBs) | 27.34 | 3.91 | 100 | 15 | Works | NOCT | Post | No | No | 09/22 | 03/23 | 32.84 | 4.69 | M/s. SAI PROJECTS (Mumbai) Pvt. Ltd. Khar (West) Mumbai-400052 | India | 25/04/23 | 24 | Under Implementation
20 | MRVC/W/132 | Construction of FOBs and Associated Works to control Mid-Section Tress passing at different locations of Mumbai division (3 FoBs) | 53 | 7.57 | 100 | 15 | Works | NoCT | Post | No | No | 03/23 | 10/23 | 50.89 | 3.36 | M/s Power Mech Projects Limited, Hyderabad | India | 2023-09-10 | 24 | Under Implementation
21 | MRVC/W/133 | Balance work of Improvement of Khar Road Station including provision of Elevated decks, inter-connections between Deck/FOBs, skywalks, relocation of service buildings, stalls, kiosks etc., improving entry/exit, improving circulating areas etc. at Khar Road Station of Mumbai division | 35 | 5 | 100 | 15 | Works | NoCT | Post | No | No | 11/22 | 03/23 | 39.72 | 5.67 | M/s. SAI PROJECTS (Mumbai) Pvt. Ltd. Khar (West) Mumbai-400052 | India | 2023-09-02 | 12 Months | Under Implementation
|  | Sub total Engineering works ( Mid Section ) | 368.29 | 52.62 | [9 empty] | 360.53 | 46.82
B |  | Electrical and Signaling works
Virar Dahanu Road
22 | MRVC/W/116 | Removal of OHE infringement in VR-DRD section | 12.18 | 1.74 | 100 | 15 | Works | NOCT | Post | No | No | 07/22 | 12/22 | 16.68 | 2.38 | M/sTexmaco Rail & Engg Ltd | India | 13.12.22 | 24 Extended upto 30.06.2025 | Under Implementation
| MRVC/W/117-A cancelled | Design, Supply, Installation, Testing and Commissioning of Indoor and Outdoor Signalling and Telecom gears involving operational requirements in concerned with quadrupling of VR-DRD section.
23 | MRVC/W/117-A-1 | Design, Supply, Installation, Testing and Commissioning of Indoor equipments/gears for Signalling works in connection with Virar (VR)-Dahanu Road (DRD) quadrupling project in Mumbai Suburban (MUTP-III) | 213.26 | 26.66 | 100 | 15 | Works | IOCT | Prior | No | No | 02/24 | 09/24 | 186.1 | 26.59 | M/s Kiran Pravesh JV | India | 10.09.2024 | 36 | Under Implementation
| MRVC/W/117-A-2 | Design, Supply, Installation, Testing and Commissioning of Outdoor equipments/gears for Signalling works and Telecommunication works in connection with Virar (VR)-Dahanu Road (DRD) quadrupling project in Mumbai Suburban (MUTP-III) | 133.39 | 16.67 | 100 | 15 | Works | IOCT | Prior | No | No | 02/24 | 09/24 | 185.2 | 26.46 | M/s Kiran Pravesh JV | India | 10.09.2024 | 36 | Under Implementation
| MRVC/W/117-B | Design, Supply, Installation, Testing and Commissioning of Telecom works involving PIS works, Ticketing works, CCTV etc. in concerned with quadrupling of VR-DRD section. | 50 | 6.25 | 100 | 15 | Works | NOCT | Post | No | No | 12/24 | 06/25 | [5 empty] | 18
| MRVC/W/117-C | Design, Supply, Installation, Testing and Commissioning of TMS works in concerned with quadrupling of VR-DRD section. | 50 | 6.25 | 100 | 15 | Works | NOCT | Post | No | No | 12/24 | 06/25 | [5 empty] | 18
24 | MRVC/W/118 | Design,Supply, Installation & Commissioning of Solar Panel for Virar –Dahanu section | 65 | 9.29 | 100 | 15 | Works | NOCT | Post | No | No | 3/25 | 10/25 | [5 empty] | 12
25 | MRVC/W/123 | Removal/Shifting/diversion of HT/LT electrical OH lines, cable crossing and allied GS works in connection with quadrupling of VR-DRD section in Mumbai Division of Western Railway under MUTP-III | 7.73 | 1.1 | 100 | 15 | Works | NOCT | Post | No | No | 09/20 | 03/21 | 6.38 | 0.91 | M/s Sankalp Industrial Services Palghar, Maharashtra | India | 18/03/2021 | 24 | Completed
26 | MRVC/W/124R | Removal/Shifting/Replacement of Signal & Telecom gears, Underground Signal & Telecom Cable/Opetical Fiber Cable(OFC) in coonection with Quadrupling of Virar - Dahanu Road section in Mumbai Division of Western Railway under MUTP-III | 11.64 | 1.66 | 100 | 15 | Works | NOCT | Post | No | No | 11/21 | 08/22 | 11.51 | 1.64 | M/s. A. R Rail Vikas Services Pvt. Ltd. Gorai Borivali (West) Mumbai | India | 28/08/2022 | 36 | Under Implementation
27 | MRVC/W/127 | LOT-1 Quadrupling Virar Dahanu road: Design, Supply ,Installation, Testing & Commissioning of OHE Est Cost - Rs. 203 Crs | 318 | 39.75 | 100 | 15 | Works | NOCT | Prior | No | No | 02/24 | 06/24 | 220.09 | 28.5843 | M/s Texmaco Rail & engineering Ltd. | India | 15.10.2024 | 36 | Under Implementation
|  | LOT-2 PNVL-KJT Suburban Corridor - Design, Supply ,Installation, Testing & Commissioning of OHE Est Cost - Rs. 115 Cr. | [11 empty] | 123.73 | 17.6757 | M/s Traxun tower India Pvt Ltd |  | 25.10.2024 | 24 | Under Implementation
28 | MRVC/W/128 | Providing General Elecrification to Proposed Station buildings, service buildings, New Platforms, New FOBs, Staff quarters, Tower wagon shed; Extension of existing platforms, existing FOBs etc. at various stations in the section between Vaitarna (Excluding ) and Dahanu (Including) in connection with Quadrupling of Virar-Dahanu Road Railway Project | 32 | 4.57 | 100 | 15 | Works | NOCT | Post | No | No | 03/23 | 06/23 | 34.07 | 4.87 | M/s Texmaco Rail & Engg Ltd Andheri Mumbai 93 | India | 12.09.2023 | 36 | Under Implementation
| MRVC/W/128A | Provision of Air-Conditioning for Relay Huts, RRI/OC and EI between VR-DRD Section under MUTP-III | 13.7 |  |  |  |  | NoCT | Post | No | No | 02/25
29 | MRVC/W/137/R | Signaling and Telecommunication works in concern with removal of S&T infringements at Virar Station of Mumbai Division of Western Railway | 4.65 | 0.66 | 100 | 15 | Works | NOCT | Post | No | No | 09/23 | 22.11.2023 | 5.73 | 0.82 | M/s Shrinath Constructions, 25, Vakharia Industrial Estate, Ram Mandir Road, Goregaon West, Mumbai -400104. | India | 22.11.2023 | 6 | Under Implementation
30 | MRVC/W/138R-Lot-I | S&T Infringement removal for construction of new station building, bridges, platforms, track works and other utilities at Saphale station in connection with Quadrupling work between Virar - Dahanu Road section of Mumbai Division of Western Railway | 8.16 | 1.17 | 100 | 15 | Works | NOCT | Post | No | No | 12/23 | 02/24 | 6.78 | 0.8475 | Ms pravesh constructions, Mumbai | India | 10.04.2024 | 6 | Under Implementation
| MRVC/W/138R-Lot-II | S&T Infringement removal for construction of new station building, bridges, platforms, track works and other utilities at Kelve Road station in connection with Quadrupling work between Virar - Dahanu Road section of Mumbai Division of Western Railway. | 8.03 | 1.15 | 100 | 15 | Works | NOCT | Post | No | No | 12/23 | 02/24 | 6.96 | 0.87 | Ms pravesh constructions, Mumbai | India | 10.04.2024 | 6 | Under Implementation
| MRVC/W/138R-1-Lot-III | S&T Infringement removal for construction of new station building, bridges, platforms, track works and other utilities at Palghar station in connection with Quadrupling work between Virar - Dahanu Road section of Mumbai Division of Western Railway | 9.65 | 1.38 | 100 | 15 | Works | NOCT | Post | No | No | 01/24 | 02/24 | - | - | - | -
| MRVC/W/138R-1-Lot-IV | S&T Infringement removal for construction of new station building, bridges, platforms, track works and other utilities at Boisar, Vangaon and Umroli station in connection with Quadrupling work between Virar - Dahanu Road section of Mumbai Division of Western Railway | 9.44 | 1.35 | 100 | 15 | Works | NOCT | Post | No | No | 01/24 | 02/24 | 9.23 | 1.1538 | M/s Shrinath Constructions,Mumbai | India | 27.03.2024 | 6 | Under Implementation
|  | Sub total Electrical and Signalling Works (Virar-Dahanu) | 946.83 | 119.65 | [9 empty] | 812.46 | 112.8012
Panvel-Karjat
| MRVC/W/119 Cancelled | Panvel Karjat Suburban Corridor: Design, Supply ,Installation, Testing & Commissioning of OHE | [12 empty] | 196.7625
31 | MRVC/W/120 | Survey, Design, Supply, Execution, Installation, Testing and Commissioning of 4 Aspect Automatic Block Signalling with Electronic Interlocking, Dual Multi Section Digital Axle Counters, UFSBI, Auxiliary Warning System and other associated Works in Panvel - Karjat Section of Mumbai Division of Central Railway. | 102.68 | 14.6686 | 100 | 15 | Works | NOCT | Post | No | No | 03/24 | 09/24 | 74.96 | 9.05 | M/S Bharat Rail Automations Pvt.Ltd. | India | 23.09.2024 | 24 | Under Implementaiton
32 | MRVC/W/121 | Design,Supply, Installation & Commissioning of Solar Panel for Panvel - Karjat | 8.43 | 1.2 | 100 | 15 | Works | NOCT | Post | No | No | 11/24 | 03/25 | [5 empty] | 24
33 | MRVC/W/130 | Panvel - Karjat suburban corridor: General electrification works for Station buildings, service buildings, Platforms, FOBs etc. | 30.5 | 3.81 | 100 | 15 | Works | NOCT | Post | No | No | 05/23 | 09/23 | 41.0994 | 5.1374 | M/s Leena Electromechinal Pvt LTd. | India | 25.01.2024 | 36 | Under Implementation
34 | MRVC/W/140 | Survey, Design, Supply, Execution, Installation, Testing and Commissioning of Telecommunication Assets consisting of Passenger Information System, Control Communication ensuring compatibility to existing Telecommunication System and other associated Works in Panvel-Karjat Section of Mumbai Division of Central Railway- in State of Maharashtra. | 16.24 | 2.32 | 100 | 15 | Works | NOCT | Post | No | No
35 | MRVC/W/141 | Survey, Design, Supply, Execution, Installation, Testing and Commissioning of Tunnel Communication and other associated Works ensuring compatibility to existing Telecommunication System in Three tunnels in connection with Panvel -Karjat double line Suburban Corridor Project of Mumbai Division of central Railway in State of Maharashtra. | 5.24 | 0.74857 | 100 | 15 | Works | NOCT | Post | No | No
|  | Subtotal Electrical and Signalling Works (Panvel-Karjat) | 163.09 | 19.6786 | [9 empty] | 116.0594 | 210.9499
Mid-Section trespass control
36 | MRVC/W/134R | Infringement Removal and execution of Signalling & Telecom works in connection with construction of FOBs to control Mid-Section Tress passing at different locations of Mumbai Division of Central Railway. | 6.54 | 0.93 | 100 | 15 | Works | NOCT | Post | No | No | 09/23 | 02/24 | 6.35 | 0.8 | M/s. Teletech Services, Mumbai | India | Under Process | 24 | Under Implementation
37 | MRVC/W/135 | OHE works Midsection Trespass at differenct location on C.Rly (10 FoBs) | 4.94 | 0.62 | 100 | 15 | Works | NOCT | Post | No | No | 04/23 | 08/23 | 5.44 | 0.68 | M/s Leena Electromechinal Pvt LTd. | India | 25.01.2024 | 24 | Under Implementation
38 | MRVC/W/136 | GS works Midsection Trespass at different location on C.Rly (10 FoBs) | 5 | 0.63 | 100 | 15 | Works | NOCT | Post | No | No | 04/23 | 08/23 | 5.46 | 0.68 | M/s Sankalp industrial servuces | India | 20.12.2023 | 24 | Under Implementation
|  | Subtotal Electrical and Signalling Works (TPC) | 16.48 | 2.18 | [9 empty] | 17.25 | 2.16
Combined works
39 | MRVC/W/122/Lot-I/A | Lot-I/A-Design,Supply, Erection, Testing & Commissioning of Boundary SP at Virar including OHE modifcation in Virar -Dahanu Road section. | 10.85 | 1.83 | 100 | 15 | Works | NOCT | Post | No | No | 03/23 | 08/23 | 9.7 | 1.39 | M/s Cimechel Andheri, Mumai | India | 28.08.2023 | 12 | Under Implementation
| MRVC/W/122/Lot-I&Lot-II | Lot-I-Design,Supply, Erection, Testing & Commissioning of TSS/SP/SSPs in Virar -Dahanu Road (Excluding Boundary SP at Virar) | 179 | 22.38 | 100 | 15 | Works | NOCT | Prior | No | No | 02/24 | 07/24 | 154.14 | 10.7898 | M/s Texmaco Rail & Engg Ltd Andheri Mumbai 93 | India | 11.10.2024 | 24 | Under Implementation
|  | Lot -II -Design,Supply, Erection, Testing & Commissioning of PSI for Panvel -Karjat corridor | 100 | 12.5 | [9 empty] | 89.13 | 6.2391 | M/s Texmaco Rail & Engg Ltd Andheri Mumbai 93 |  | 26.11.2024 | 24 | Under Implementation
40 | MRVC/W/126R | Design and Preparation of Signalling documents like Signalling plans, Control Tables, SWR diagrams etc. and Checking of Logic Circuit/Wiring Diagrams | 6 | 0.86 | 100 | 15 | Works | NOCT | Post | No | No | 03/22 | 09/22 | 4.24 | 0.2968 | M/s. Shrinath Constructions Goregaon West Mumbai | India | 23/9/2022 | 60 | Under Implementation

## III-Goods
Project Name: Mumbai Urban Transport Project III
Procurement Plan: Goods
| Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [13 empty] | Revision No: 17 |  | 07.04.2025 |  |  |  | 4
Specific Procurement Arrangements | [11 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status | Remarks/Status of Work
Serial No. | Contract No. | Description of Contract | Cost Estimate in Local Currency without GST (In INR crore) | Cost Estimate in USD (In million) | Funding* Source by AIIB (%) (Excluding Taxes) | Funding* Source by Others (%) (includes Taxes & Rly Funding) | Procurement Category | Procurement Method (IOCT/DC/ST/ NCT/ RFQ) | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency with GST (In INR crore) | Contract Price Equivalence in USD (In million) | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
Goods
Virar-Dahanu Raod and Panvel-Karjat Combined
1 | MRVC/G/101A | Supply, Installation & Commissioning of Escalator for various locations/stations on WR-Virar-Dahanu section & on CR-Panvel-Karjat section [LOT-I for WR (24 Nos), LOT-II for CR (34 Nos).] | 30.67 | 3.94 | 100 | 15 | Goods | NOCT | Post | No | No | 11/24 | [6 empty] | 27 |  | Tender under finalisation
| MRVC/G/101B | Supply, Installation & Commissioning of Elevators for various locations/stations on WR-Virar-Dahanu section & on CR-Panvel-Karjat section along with Staff Quarters and Service Bldg of CR [LOT-I for WR (27 Nos), LOT-II for CR (17 Nos) & LOT-III for CR (07 Nos)] | 8.99 | 1.17 |  |  | Goods | NOCT | Post | No | No | [9 empty] | Tender under finalisation
| MRVC/GS/101/R/LOT-I/Elev/VR-DRD/Qtrs & Serv. Bldg | Procurement of Elevators (Design, Manufacture, Supply, erection, Commissioning & Maintenance of Elevators for Residential Quarters, RRI/RPF, Service Bldg in VR-DRD Section (31 Nos) | 5.19 | 0.75 |  |  | Goods | NOCT | Post |  |  | 09/24 |  | 4.21 | 1.23 | M/s. Omega Elevators |  |  | 36 |  | LOA issued on 22.11.2024. GAD for 11 locations approved. Material for 8 lifts recieved and under installation at Virar, saphale, kelve and palghar
2 | MRVC/G/103 | Supply, assemble, Installation &Commissioning of Tower Wagon | 19 | 2.71 | 100 | 15 | Goods | NOCT | Post | No | No | 12/24 | 07/25 | [5 empty] | 24
3 | MRVC/G/104 | Supply,assemble, Installation & Commissioning of Wiring Train | 58 | 8.29 | 100 | 15 | Goods | IOCT | Prior | No | No | 12/24 | 07/25 | [5 empty] | 24
4 | MRVC/G/105 | Supply, assemble,Installation & Commissioning of OHE maintainence vehicle | 7 | 1 | 100 | 15 | Goods | NOCT | Post | No | No | 12/24 | 04/25 | [5 empty] | 24 |  | Tender invited , to be opened on 14.5.2025
5 | MRVC/G/106 | Supply, Installation & Commissioning of PSI Van | 7 | 1 | 100 | 15 | Goods | NOCT | Post | No | No | 12/24 | 04/25 | [5 empty] | 24 |  | BOQ under finance Vetting
6 | MRVC/G/108 | Supply , transporting and stacking of PSC wide base main line sleepers, Special guard rail sleeprs for Bridge, Bridge approach sleepers and SEJ sleeprs for the project of Quadrupling of Virar Dahanu Raod and Panvel-Karjat - New suburban Corridor under MUTP-III |  |  | 100 | 15 | Goods | IOCT | Prior | No | No | [9 empty] | Tender opened on 12.05.2024. TER sent & approved by AIIB on 17.05.2024. Notification to Intenet to award on 24.05.2024. L.O.A issued on 05.06.2024
|  | Lot-I: In the section between Virar and Dahanu Road stations on Mumbai suburban section of Western Railway. | 92.46 | 13.21 | [7 empty] | 12/23 | 5/24 | 95.99 | 13.7129 | M/s. Patil Rail Infrastructure Pvt. Ltd. | India |  | 12
|  | Lot-II: In the section between Panvel to Karjat stations on Mumbai suburban section of Central Railway for new suburban corridor. | 48.25 | 6.89 | [9 empty] | 51.99 | 7.4271 | Bemco-Raghavendra (JV) | India |  | 6
|  | Sub Total Combined Goods | 271.37 | 38.21 | [9 empty] | 147.98 | 21.14
Mid-Section Tress pass control
7 | MRVC/G/107 | Supply, Installation & Commissioning of Escalator for MUTP-III Mid section Trespass Control works | 9.98 | 1.43 | 100 | 15 | Goods | NoCT | Post | No | No | 07/22 | 10/22 | 9.61 | 1.23 | Johnson Lifts Pvt. Ltd, Chennai | India | 20.10.2022 | 18 months Extended upto 19.04.2025 | Under Implementation | All 4 Escalators at Khar Rd supllied and commissioned, 6 escalators of Ghatkopar commissioned. GAD for 04 nos. at BUD approved.
|  | Sub Total Mid-Section Tress pass control | 9.98 | 1.43 | [9 empty] | 9.61 | 1.23
|  | Total of Goods and Plants | 281.35 | 39.64 | [9 empty] | 157.59 | 22.37
Notes: 1) *Funding of basic cost is considered from AIIB while all taxes and statutory deductions are considered on part of counter part. Accordingly indicative funding % are shown. In advance contracts it will vary depending upon payment already made
Notes: 2) Exchange rate (USD 1: INR 70)

## III-Cons-TA Studies
Procurement Plan: Consultancies
| Project Implementation Entity: Mumbai Railway Vikas Corporation Ltd., Mumbai, India | [15 empty] | Revision No: 17 |  | Revision Date: 07.04.2025
Specific Procurement Arrangements | [11 empty] | Scheduled Dates |  | Contract Award Details | [5 empty] | Contract Implementation Status | Remarks/Status of Work
Serial No. | Contract No. | Description of Contract | Cost Estimate in Local Currency (In INR crore) | Cost Estimate in USD (In million) | Funding* Source by AIIB (%) (Excluding Taxes) | Funding* Source by Others (%) (includes Taxes & Rly Funding) | Procurement Category | Procurement Method (IOCS/ NCS/ LC/ DS) | Review by Bank (Prior or Post) | Pre-qualification (Yes/No) | Advance Contracting (Yes/No) | Tender Invitation (MM/YY) | Contract Signing (MM/YY) | Contract Price in Local Currency (In INR crore) | Contract Price Equivalence in USD (In million) | Contractor’s Name | Origin of Country | Contract Signing Date | Contract Period (Months)
(A) Consultancy Services chargeable to Project i.e., Components A, B, & C
1 | MRVC/MUTP- III/Consultancy/GC/01/2019/101 | General Consultancy Services (GC) for MUTP-III Projects covering Bid Process Management and Project Management Services | 104.8 | 14.97 | 100 | 15 | Consultancy | IOCT | Prior | Yes | Yes | 06/19 | 12/19 | 104.8241 | 14.97 | M/s. Rodic Consultants Pvt. Ltd in JV with M/s. Artelia Ville & Transport 1, Jai Singh Road, First Floor., New Delhi | India | 18/12/2019 | 72 | Under Implementation | Work in progress.
2 | MRVC/RFP/W/MUTP III/2016/99/R1/VR-DRD | Detailed Design Engineering (including PMC of designs) for Quadrupling of Virar-Dahanu Road Project (64 Km) on Western Railway BCT Division. | 10.59 | 1.51 | 100 | 15 | Consultancy | IOCT | Post | Yes | Yes | 04/16 | 09/16 | 10.5925 | 1.51 | M/s AECOM Asia Company Ltd. In JV with Consulting Engineering Group Ltd. , Gurgaon, Haryana | India | 27/09/2016 | 66 | Under Implementation | Advance Contract Work in progress. EOT granted till 31.03.2027 for the work.
3 | MRVC/RFP/W/MUTP III/2016/99/R1/PNVL-karjat & Airoli-Kalwa | Detailed Design Engineering (including PMC of designs) for Double line Corridor between Panvel - Karjat (33 Km) and Elevated Double Line Rail Link between Airoli Kalwa (4 KM) On Central Railway. | 11.2 | 1.6 | 100 | 15 | Consultancy | IOCT | Post | Yes | Yes | 04/16 | 09/16 | 11.2232 | 1.6 | M/s AECOM Asia Company Ltd. , Gurgaon, Haryana | India | 27/09/2016 | 66 | Under Implementation | Advance Contract Work in progress. Part B extension till 31.12.2025
4 | MRVC/RFP/W/MUTP- 3/EA/2015/99 | Consultancy for “Environmental Assessment (EA) of all components of MUTP-III Projects”. | 1.14 | 0.16 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 12/15 | 07/16 | 1.142 | 0.16 | M/s. IL & FS Environmental Infrastructure & Services Ltd. In Association with M/s. STEP Andheri, Mumbai, Maharashtra | India | 2016-11-07 | 18 | Completed | Advance Contract Completed. Report was approved by AIIB uploaded on MRVC website on 23/05/2019
5 | MRVC/RFP/W/MUTP- 3/SM/2010/109 | Consultant for “Preparatory Social Management Activities for MUTP-III Projects”. | 0.46 | 0.07 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 06/16 | 12/16 | 0.45109 | 0.06 | Firm M/s. Voyants Solutions Pvt. Ltd. Gurgaon, Haryana | India | 30/12/2016 | 12 | Completed | Advance Contract Completed. Report was approved by AIIB uploaded on MRVC website on 17/05/2019
6 | MRVC/RFP/W/MUTP- 3/2016/99 | Consultancy Services for detailed Design Engineering “for mid-section Trespass Control measures in Mumbai Suburban sections”. | 3.53 | 0.5 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 09/15 | 04/16 | 3.5359 | 0.51 | Firm M/s. Padeco Co. Ltd (Lead Partner) & Amiand Consulting Pvt. Ltd. JV Santacruz, Mumbai, Maharashtra | India | 2016-04-04 | 45 | Completed | Advance Contract Completed
|  | Sub Total (A) | 131.72 | 18.81 | [9 empty] | 131.7688 | 18.81
(B) TA Studies (Component D) i.e., Other Studies / Institutional strengthening Consultancies
| B-I | TA Studies already awarded
7 | MRVC/RFP/2018/ Maint. Facility | Ascertaining the maintenance facility requirement on western and Central railway for increased holding of emu rakes after MUTP-III and other projects | 2.11 | 0.3 | 100 | 15 | Consultancy | IOCT | Post | Yes | Yes | 04/18 | 01/19 | 2.12 | 0.3 | M/s.Pedaco Co Ltd. Japan(Lead Partner) and M/s. Ardanuy Ingenierie Madrid, 6-17-19 Shinbashi Minato-ku, Tokyo | Japan / Spain | 2019-04-01 | 18 | Completed | Contract Completed. Final report sent to AIIB on 04/Apr/2023 & approved by AIIB on 27/Apr/2023.
8 | MRVC/RFP/2018/Elect./IGBC | Study of Benchmarking environmental performance of Mumbai Suburban Rail System. | 0.22 | 0.03 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 03/18 | 12/18 | 0.22 | 0.03 | M/s. IRG System South Asia Pvt. Ltd. E-16, 3rd Floor , main market, Hauz Khas, New Delhi | India | 2018-03-12 | 6 | Completed | Contract Completed. Final report sent to AIIB on 28/Jan/2020 & approved by AIIB on 12/Feb/2020
9 | MRVC/RFP/2018/RS/Leasing | Consultancy for leasing rolling Stock leasing market for procurement of EMU Trains for mumbai suburban | 1.55 | 0.22 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 04/18 | 09/18 | 1.56 | 0.22 | M/s. ERNST & young LLP (in JV with M/s. LEAP Infraays Pvt. Ltd. (LIPL), Faridabad, Kolkata, West Bengal | India | 25/09/2018 | 12 | Completed | Contract Completed. Final report sent to AIIB on 06/Jun/2020 & approved by AIIB on 29/Jul/2020.
10 | MRVC /RFP/W/MUTP-3/PNVL -VR/EIA & EMP/2017 | Consultancy for "Environmental Impact Assessment (EIA) of Panvel -Virar Suburban corridor Project". | 0.73 | 0.1 | 100 | 15 | Consultancy | NOCT | Post |  |  | 01/18 | 08/18 | 0.73 | 0.1 | Firm M/s. URS Scott Wilson India Private Gurgaon, Limited Haryana | India | 2018-10-08 | 9 | Completed | Advance Contract Short Closed.
11 | MRVC /RFP/W/184/PNVL -VR/SIA /Consultancy/2018 | Selection of Consultant for Social Impact Assessment (SIA) and preparation of Social Management Plan (SMP) for Panvel-Virar New Suburban Corridor Project | 0.25 | 0.04 | 100 | 15 | Consultancy | NOCT | Post |  |  | 04/18 | 11/18 | 0.25 | 0.04 | M/s. Centre for Market Research and Social Development Pvt. Ltd. Associated with M/s. Manavadhikar Samajik Manch, New Delhi | India | 16/11/2018 | 9 | Completed | Advance Contract Short Closed.
12 | MRVC/TA/112 | Interim Consultancy Services for PNVL-Virar New Suburban Corridor | 5.96 | 0.85 | 0 | 100 | Consultancy | [5 empty] | 02/18 | 7.03 | 1 | Contract awarded M/S. RITES Limited, Gurgaon by direct selection | India | 19/02/2018 |  | Completed | Counterpart Funding
13 | MRVC/TA/113 | Interim Consultancy Services for fast corridor on CSTM-Panvel Harbour line including Airport Spur | 5.3 | 0.76 | 0 | 100 | Consultancy | [5 empty] | 09/17 | 6.25 | 0.89 | Contract awarded M/S. RITES Limited, Gurgaon by direct selection | India | 27/09/2017 | 12 | Completed | Counterpart Funding
14 | MRVC/TA/114 | Preparation to technical document for Vashi Creek bridge including approaches for Fast Corridor CSTM-Panvel. | 0.17 | 0.02 | 0 | 100 | Consultancy | [5 empty] | 02/18 | 0.19 | 0.03 | Contract already awarded to M/s. SCG Consultancy Services, Mumbai | India | 20/02/2018 | 4 | Completed | Counterpart Funding
15 | MRVC/TA/115 | Consultancy for Feasibility report of Extension of Harbour Line from Goregaon to Borivali and provision of 5th / 6th line between Borivali to Virar | 0.36 | 0.05 | 0 | 100 | Consultancy | [5 empty] | 12/17 | 0.42 | 0.06 | Contract awarded M/S. RITES Limited, Gurgaon by direct selection | India | 21/12/2017 | 1 | Completed | Counterpart Funding
16 | MRVC/TA/116 | Feasibility study for Underground Suburban Rail Corridor between CSMT and Thane in Mumbai | 1.02 | 0.15 | 0 | 100 | Consultancy | [5 empty] | 05/18 | 1.2 | 0.17 | Contract awarded by Railway Board to Delhi Metro Rail Corporation Limited (New Delhi) | India | 2018-03-05 | 12 | Completed | Counterpart Funding
17 | MRVC/TA/120 | Project Management Information System (PMIS) and Integrated interactive Graphical User Interfaces representation for projects under execution by MRVC | 4.2 | 0.6 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 10/19 | 08/20 | 10 | 1.5 | M/s Synergiz Global Services Pvt. Ltd.Jubilee Hills, Hyderabad | India | 19/08/2020 | 60 | Under Implementation | All PMIS modules have been developed and MUTP III & IIIA projects have been mapped on PMIS for monitoring. To make the PMIS more effecetive and wholesome, electronic billing has been developed and is currently under testing. This will eliminate the manual bill processing. Contractor issues module added. Variation processed on 25.02.2025.
18 | MRVC/TA/124 | Study of Crowding survey at stations, Simulation studies and measures to reduce congestion and improve passenger flow at stations on Mumbai suburban system | 6.26 | 0.9 | 100 | 15 | Consultancy | IOCT | Post | Yes | No | 11/19 | 03/22 | 7.38 | 1.05 | Firm M/s PEDACO Company Ltd. Minato-ku Tokyo | Japan | 15/03/2022 | 6 | Under Implementation | 1. Inception Report Submitted. 2. Preliminary reports for all 49 stations with all deliverables (Topo, Passenger Counts, Station Planning, Simulation study, Siganges, CCTV-PAPS and Illumination report) submitted. 3. Final Report for -Topo, Passenger Counts, , CCTV-PAPS and Illumination report - All 49 stations submimitted. 4. Final Report for - Station Planning for 9 stations and Simulation study for 3 stations submimitted. 5. Final Report for- Station Planning for 40 stations and Simulation study for 14 stations in Progress
19 | MRVC/TA/125 MRVC/Station Improvement/2018 | Consultancy for Detailed Planning for Improvement of Identified Suburban Railway Stations of Central and Western Railway in Mumbai including Surveys, Architectural and Passenger Movement Plans, Preparation of GADs, Specifications and Cost Estimations etc. | 1.75 | 0.25 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 11/18 | 06/19 | 1.76 | 0.25 | Intercontinental Consultants & Technocrats Pvt. New Delhi in consortium with M/s Gian P. Mathur & Associates Pvt. Ltd. , New Delhi | India | 2019-07-06 | 8 | Closed | Work Completed. Final Report submitted by Consultant & same shared with AIIB.
20 | MRVC/TA/126 | Third party Environmental and Social Monitoring of the implementation of SIAs, ESMPs, and CESMPs and the Resettlement action plan and evaluate the compliance of the project activities for the projects of MUTP-III as per TOR | 0.8 | 0.11 | 100 | 15 | Consultancy | NOCT | Post | Yes | No | 11/20 | 08/21 | 1.05 | 0.15 | M/s. URS Scott Wilson India Pvt. In JV with AECOM India Pvt. Ltd.,Gurgaon, Haryana | India | 2021-11-08 | 60 | Under Implementation | Work in progress. Third party half yearly reports are shared with AIIB till Jan-June 24.
21 | MRVC/TA/127 | Aerial videography, (Ortho photo/Photometry survey for the projects of MUTP-III mentioned in TOR for monitoring progress of the work. | 0.55 | 0.08 | 100 | 15 | Consultancy | NOCT | Post | Yes | No | 08/20 | 02/21 | 0.56 | 0.08 | M/s. Indrones Solutions Pvt. Ltd. , Navi Mumbai, Maharashtra | India | 24/02/2021 | 60 | Under Implementation | Work in progress. Links for VR-DRD & PNVL-KJT photos/videos are shared with AIIB from time to time.
22 | MRVC/TA/128 | Detail Design consultancy work for Vasai creek Bridges No. 73 (28 X 48.3m span) and Bridge no. 75 (11 X 48.3m span) in between Bhayandar and Naigaon stations in connection with 5th and 6th line between Borivali and Virar. | 3.01 | 0.43 | 100 | 15 | Consultancy | NOCT | Post | Yes | No | 01/21 | 08/21 | 3.51 | 0.5 | M/s. Shirish Patel & Associates (Mumbai) | India | 16/06/2022 | 42 | Under Implementation | Preliminary design and DBR prepared andapproved. Consultant has submitted preliminary design for entire bridge, which is under proof checking of Third Party Consultant i.e. Konkan Railway Corporation Ltd.
23 | MRVC/TA/130 | Implementation of National Common Mobility Card (NCMC) based Automatic Fare Collection System on Mumbai Suburban Railway Network of Western & Central Railways | 1.14 | 0.16 | 100 | 15 | Consultancy | Limited Tender | Post | No | No | 12/21 | 05/22 | 0.74 | 0.11 | M/s. Ernts & Young LLP Gujarat, India | India | 44900 | 9 | work short closed | work is short closed
24 | MRVC/TA/122 | Technical assistance study for instrumentation of new proposed Vaitarana Bridge and one major bridge with PSC super structure for real time monitoring of health – sub structure and super structure in connection with ‘MUTP- III project. | 0.5 | 0.07 | 100 | 15 | Consultancy | NOCT | Post | Yes | No | 11/21 | 05/22 | 0.94 | 0.13 | M/s. Aarvee Associates Architects Engineers & Consultants Pvt. Ltd. in association with Starmass Environment Technologies. | India/ Canada | 2022-08-07 | 4 | Under Implementation | Show cause notice to Aarvee associates consultant has been sent regarding TA studies and is instructed to submit the action plan within 2 weeks.
25 | MRVC/CBTC/ Consultancy/GC/01/2019 (MRVC/Cons./221) | CBTC-Procurement of Consulting Services for preparation of technical specification & Bid Management for “Implementation of CBTC (Communication Based Train Control) system to enhance safety and to achieve improved headway on Mumbai Suburban Railway network of Western & Central Railways” | 11 | 1.57 | 100 | 15 | Consultancy | NOCT | Post | Yes | Yes | 11/19 | 08/20 | 10.5 | 1.5 | Systra S.A (Lead Partner of JV) France in JV with Systra MVA Consulting (India) Pvt. Ltd., Fridabad, Hayana | France India | 28/08/2020 | 12 | Under Implementation | Transferred from MUTP-IIIA as agreed by AIIB. Technical specifications and functional requirements submitted by the consultant. Validity extended till 31-03-2025.
26 | MRVC/TA/119 | Study for Migration Strategy to be adopted while inducting Air- Conditioned EMU rakes in Mumbai Suburban section of Central & Western Railway. | 1.31 | 0.19 | 100 | 15 | Consultancy | NOCT | Post | Yes | No | 11/21 | 12/22 | 1.17 | 0.14 | Systra MVA Consulting (India) Pvt. Ltd. JV with Systra (France) | France / India | 2022-12-02 | 17 | Under Implementation | Contract period is extended upto 31.05.2025. Final report recieved.
|  | Sub total of TA Studies already awarded (B-I) | 35.38 | 5.05 | [9 empty] | 42.49 | 6.1
| B-II | TA Studies under porcess
27 | MRVC/TA/123 | Training, Seminar, conferences, workshop, other capacity building measures etc | 15 | 2.14 | 100 | 15 | Others as per requirement | [6 empty] | 0 | 0 | [5 empty] | Formal Procurement Procedure is not applicable.
|  | Sub total of TA Studies under process (B-II) | 15 | 2.14 | [9 empty] | 0 | 0
|  | Sub total of TA Studies ( B= B-I + B-II) | 50.38 | 7.19 | [9 empty] | 42.49 | 6.1
|  | Gand Total of Consultancies/TA Studies (A+B) | 182.1 | 26 | [9 empty] | 174.2588 | 24.91
Notes: 1) *Funding of basic cost is considered from AIIB while all taxes and statutory deductions are considered on part of counter part. Accordingly indicative funding % are shown. In advance contracts it will vary depending upon payment already made
Notes: 2) Exchange rate (USD 1: INR 70)