## Publication
P000871 Karakalpakstan and Khorezm Local Roads Network Rehabilitation Project
Project Country: | Uzbekistan | Bank's Approval Date of the Initial Procurement Plan: | 07-10-2025
Project Sector: | Transport | Approved PP Update No.: | Version 6
AIIB Loan (USD Million): | 173.48 | Bank's Approval Date of the PP Update: | 12-12-2025
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Contract Duration (Days) | Activity Status
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-02/Lot-4 | The project involves reconstruction of Lot 4 - 57,1 km in Kungrad. Contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. | 10,700,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 08-25-2025 | 01-30-2026 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-02/Lot-3 | The project involves reconstruction of Lot 3 – 92 km in Shomanay, Kanlikol, Moynaq, Xozheyli. Contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. | 24,000,000.00 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 08-25-2025 | 01-30-2026 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-02/Lot-2 | The project involves reconstruction of Lot 2 –83 km in Kegeyli, Shimbay, Nukus, Tahtakuprik, Karauzak; Contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. | 29,400,000.00 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 08-25-2025 | 01-30-2026 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-01/Lot-3 | The project involves reconstruction of Lot 3 – 74 km in Urgench, Shavat, and Gurlan. Contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. Key qualification criteria apply per Lot and are cumulative if bidding for multiple Lots. | 23,970,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-09-2025 | 01-10-2026 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-01/Lot-2 | The project involves reconstruction of 188 km of Lot 2 – 56 km in Khiva and Koshkopir. Contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. Key qualification criteria apply per Lot and are cumulative if bidding for multiple Lots. | 19,490,000.00 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-09-2025 | 01-10-2026 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-IND-01 | Environmental & Social Consultant with OHS Focus | 55,200.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 11-14-2025 | 12-22-2025 | 14 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-IND-02 | Individual Gender Consultant | 55,200.00 | 100.00 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 11-14-2025 | 12-22-2025 | 14 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP/QCBS/3.1 | Geospatial Information System (GIS) Platform | 470,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 12-15-2025 |  | 0 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP/LCS/01 | The оvеrаIl objective of the assignment is to assist the Gоvеrnmепt of Uzbekistan to identify, assess, and implement environmental and social management measures in respect of the proposed project's interventions. То achieve this objective, it is proposed to conduct comprehensive social and environmental assessments so as to enable the рrераrаtiоп of ап ESMPF | 100,000.00 | 100.00 | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 04-29-2024 | 09-26-2024 | 14 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-02 | The project involves reconstruction of 328.1 km of local roads in Karakalpakstan, divided into 4 Lots: Lot 1 – 96 km in Amudarya, Beruniy, Tortkol, and Ellikqala; Lot 2 –83 km in Kegeyli, Shimbay, Nukus, Tahtakuprik, Karauzak; Lot 3 – 92 km in Shomanay, Kanlikol, Moynaq, Xozheyli. Lot 4 - 57,1 km in Kungrad. Each contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. | 97,245,925.00 |  | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 08-25-2025 | 01-25-2026 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | KKLRNP-CW-01 | The project involves reconstruction of 188 km of local roads in Khorezm region, divided into 3 Lots: Lot 1 – 58 km in Bagat, Hazarasp, Yangiarik, and Yangibazar; Lot 2 – 56 km in Khiva and Koshkopir; Lot 3 – 74 km in Urgench, Shavat, and Gurlan. Each contract spans 5 years, including 1095 days for construction and 730 days for the Defects Notification Period. Key qualification criteria apply per Lot and are cumulative if bidding for multiple Lots. | 61,041,000.81 | 100.00 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 07-09-2025 | 12-11-2025 | 28 | Cleared
“Avtoyo’invest” Agency under the Committee for Roads | 2.1 | Construction Supervision Consultant (CSC) | 4,279,220.00 |  | Consulting Services | IOCS (International Open Competitive Selection) | QCBS (Quality Cost Based Selection) |  | Prior |  | 07-15-2025 | 12-09-2025 | 14 | Cleared
|  | Total: | 270,806,545.81