## Publication - P000378
P000378 COVID-19 Emergency Response and Health Systems Preparedness Project
Project Country: | Maldives | Bank's Approval Date of the Initial Procurement Plan: | 02-19-2025
Project Sector: | CRF-Public Health | Approved PP Update No.: | Version 2
AIIB Loan (USD Million): | 7.3 | Bank's Approval Date of the PP Update: | 03-30-2026
PROJECT PROCUREMENT PLAN
Project Implementing Entity | Contract Number | Contract Description | Cost Estimate in USD | AIIB financing (%) | Procurement Category | Procurement Method | Particular Selection Method | Evaluation Criteria | Bank Review (Prior/Post) | Pre-qualification (Yes/No) | Expected Date of Advertisement | Expected Date of Contract Signing | Activity Status
Ministry of Health, Maldives | ERHSPP-CS-05A | Procurement of Environmental and Social Specialist | 16500 | 100 | Consulting Services | LCSIC (Limited Competitive Selection of Individual Consultants) |  |  | Post |  | 04-07-2026 | 05-15-2026 | Cleared
Ministry of Health, Maldives | ERHSPP-CS-05 | Procurement of Environmental and Social Specialis | 40661.48 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 03-24-2025 | 05-20-2025 | Cancelled
Ministry of Health, Maldives | ERHSPP-CS-04 | Procurement of Financial Management Specialist | 36231.52 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 03-24-2025 | 05-20-2025 | Cleared
Ministry of Health, Maldives | ERHSPP-CS-03 | Procurement of Project Manager | 43346.3 | 100 | Consulting Services | OCSIC (Open Competitive Selection of Individual Consultants) |  |  | Prior |  | 03-24-2025 | 05-20-2025 | Cleared
Ministry of Health, Maldives | ERHSPP-CS-02 | Procurement of Internal Auditor | 10000 | 100 | Consulting Services | LC (Limited Competition) | LCS(Least Cost Based Selection) |  | Prior |  | 10-01-2025 | 12-23-2025 | Cleared
Ministry of Health, Maldives | ERHSPP-CS-01 | IPC Training for Nurses and Doctors | 43924 | 100 | Consulting Services | DS(Direct Selection) |  |  | Prior |  |  | 04-02-2025 | Cleared
Ministry of Health, Maldives | ERHSPP-CW-01 | Establishment of Quarantine Facility - Kulhudhufushi Regional Hospital | 2650000 | 100 | Works | IOCT (International Open Competitive Tendering) |  | Lowest Evaluated Cost | Prior | No | 02-24-2025 | 05-29-2025 | Cleared
|  | Total: | 2840663.3